## summary
group | concept | year1 | year2 | total
materials and services | ISO TC69 Standards subscription | 2700 | 3250 | 5950
materials and services | AIAG Manuals acquisition | 300 | 0 | 300
materials and services | Shiny server | 440 | 440 | 880
materials and services | github | 0 | 0 | 0
materials and services | Development laptop | 1099.3334 | 0 | 1099.3334
people | Senior researchers | 7273.6 | 4727.84 | 12001.44
people | junior researcher | 15757 | 15757 | 31514 | 43515.44
travel | R/Stats conferences | 1000 | 3000 | 4000 | 0.60195
travel | ISO/Industry events | 1000 | 3000 | 4000
direct | Total direct costs | 29569.9334 | 30174.84 | 59744.7734
indirect | Indirect costs (21%) | 6209.686 | 6336.7164 | 12546.4024
total | Total cost | 35779.6194 | 36511.5564 | 72291.1758

## WP
wp | title | starts | ends | milestones
WP1 | Infrastructure building | M1 | M3 | Github repo with classes, data structures and shiny basic demo
WP2 | Infrastructure development | M4 | M21 | Progress reports, github package releases for each group of methods
WP3 | Infrastructure deployment and validation | M7 | M24 | CRAN submits and shiny app update for each group of methods
WP4 | Dissemination and coordination | M1 | M24 | Dissemination activities for each group of methods

## tasks
WP | Task | Task title | starts | ends | hours | senior_hours_y1 | junior_hours_y1 | senior_hours_y2 | junior_hours_y2 | S1 | J1 | S2 | J2 | S3 | J3 | S4 | J4 | S5 | J5 | S6 | J6 | S7 | J7 | S8 | J8 | S9 | J9 | S10 | J10 | S11 | J11 | S12 | J12 | S13 | J13 | S14 | J14 | S15 | J15 | S16 | J16 | S17 | J17 | S18 | J18 | S19 | J19 | S20 | J20 | S21 | J21 | S22 | J22 | S23 | J23 | S24 | J24
WP1 | T1.1 | Standards' Library building | M1 | M1 | 21 | 5 | 16 | 0 | 0 | 5 | 16
WP1 | T1.2 | Configure R Studio project, github repo, mail list, and webpage | M1 | M1 | 23 | 8 | 15 | 0 | 0 | 8 | 15
WP1 | T1.3 | Implement quality data standard | M1 | M1 | 30 | 6 | 24 | 0 | 0 | 6 | 24
WP1 | T1.4 | Define and document classes and generic methods | M1 | M2 | 58 | 10 | 48 | 0 | 0 | 6 | 18 | 4 | 30
WP1 | T1.5 | Define and document standards' verification process | M2 | M3 | 82 | 12 | 70 | 0 | 0 |  |  | 6 | 30 | 6 | 40
WP1 | T1.6 | Define and document functions common structure | M2 | M3 | 53 | 8 | 45 | 0 | 0 |  |  | 4 | 20 | 4 | 25
WP1 | T1.7 | Build shiny basic demo | M3 | M3 | 48 | 8 | 40 | 0 | 0 |  |  |  |  | 8 | 40
WP2 | T2.1 | Implementation of Control Charts Standards | M4 | M6 | 350 | 48 | 302 | 0 | 0 | [6 empty] | 16 | 86 | 16 | 108 | 16 | 108
WP2 | T2.2 | Implementation of Capability Analysis Standards | M7 | M9 | 308 | 42 | 266 | 0 | 0 | [12 empty] | 14 | 60 | 14 | 94 | 14 | 112
WP2 | T2.3 | Implementation of Measurement Systems Analysis Standards | M10 | M14 | 520 | 32 | 244 | 20 | 224 | [18 empty] | 12 | 60 | 10 | 72 | 10 | 112 | 10 | 112 | 10 | 112
WP2 | T2.4 | Implementation of Acceptance Sampling Standards | M15 | M19 | 513 | 0 | 0 | 50 | 463 | [28 empty] | 10 | 55 | 10 | 76 | 10 | 100 | 10 | 116 | 10 | 116
WP2 | T2.5 | Analysis and Implementation of other techniques Standards | M20 | M21 | 171 | 0 | 0 | 16 | 155 | [38 empty] | 8 | 110 | 8 | 45
WP2 | T2.6 | github major releases (at least for each group) | M4 | M21 | 48 | 6 | 18 | 6 | 18 | [6 empty] | 2 | 6 |  |  |  |  | 2 | 6 |  |  |  |  | 2 | 6 | [8 empty] | 2 | 6 | [8 empty] | 2 | 6 | 2 | 6
WP3 | T3.1 | Validation of implemented methods | M7 | M24 | 360 | 14 | 30 | 20 | 296 | [12 empty] | 8 | 20 |  |  |  |  | 6 | 10 | [8 empty] | 4 | 20 | [10 empty] | 4 | 20 | 4 | 64 | 4 | 106 | 4 | 86
WP3 | T3.2 | Releases to CRAN | M8 | M24 | 120 | 10 | 38 | 12 | 60 | [14 empty] | 2 | 18 |  |  |  |  | 8 | 20 | [8 empty] | 4 | 20 | [8 empty] | 4 | 20 |  |  |  |  | 4 | 20
WP3 | T3.3 | Shiny UI design for each method (validation) | M10 | M24 | 66 | 2 | 20 | 4 | 40 | [18 empty] | 2 | 20 | [8 empty] | 2 | 20 | [12 empty] | 2 | 20
WP3 | T3.4 | Shiny UI design for each method (new data) | M11 | M24 | 66 | 2 | 20 | 4 | 40 | [20 empty] | 2 | 20 | [8 empty] | 2 | 20 | [10 empty] | 2 | 20
WP3 | T3.3 | Minor Releases to github | M21 | M24 | 16 | 0 | 0 | 4 | 12 | [44 empty] | 2 | 6 | 2 | 6
WP4 | T4.1 | WP1 Training and coordination | M1 | M3 | 154 | 28 | 126 | 0 | 0 | 12 | 55 | 8 | 48 | 8 | 23
WP4 | T4.2 | WP1 reporting and dissemination | M4 | M4 | 20 | 4 | 16 | 0 | 0 | [6 empty] | 4 | 16
WP4 | T4.3 | WP2 training and coordination | M4 | M21 | 231 | 47 | 104 | 22 | 58 | [6 empty] | 8 | 20 | 8 | 20 | 7 | 20 | 4 | 8 | 4 | 8 | 4 | 6 | 4 | 8 | 4 | 8 | 4 | 6 | 4 | 8 | 4 | 8 | 2 | 6 | 2 | 6 | 2 | 6 | 2 | 6 | 2 | 6 | 2 | 6 | 2 | 6
WP4 | T4.4 | WP2 reporting and dissemination | M7 | M21 | 102 | 12 | 42 | 8 | 40 | [12 empty] | 4 | 26 |  |  |  |  | 8 | 16 | [8 empty] | 4 | 15 | [10 empty] | 4 | 25
WP4 | T4.5 | WP3 training and coordination | M7 | M24 | 168 | 12 | 44 | 30 | 82 | [12 empty] | 2 | 8 | 2 | 8 | 2 | 6 | 2 | 8 | 2 | 8 | 2 | 6 | 2 | 8 | 2 | 8 | 2 | 6 | 2 | 6 | 2 | 6 | 2 | 6 | 2 | 6 | 2 | 6 | 2 | 6 | 4 | 8 | 4 | 8 | 4 | 8
WP4 | T4.6 | WP3 reporting and dissemination | M8 | M24 | 72 | 4 | 8 | 12 | 48 | [16 empty] | 2 | 4 |  |  |  |  | 2 | 4 | [8 empty] | 4 | 16 | [8 empty] | 4 | 16 | 2 | 8 | 2 | 8
[5 empty] | 3600 | 320 | 1536 | 208 | 1536 | 37 | 128 | 22 | 128 | 26 | 128 | 30 | 128 | 24 | 128 | 23 | 128 | 34 | 128 | 22 | 128 | 22 | 128 | 36 | 128 | 26 | 128 | 18 | 128 | 16 | 128 | 16 | 128 | 26 | 128 | 20 | 128 | 18 | 128 | 14 | 128 | 14 | 128 | 14 | 128 | 26 | 128 | 16 | 128 | 12 | 128 | 16 | 128
[8 empty] | 528 | 3072
[6 empty] | 7273.6 |  | 4727.84

## People
Group | Name | Affiliation
senior researcher | Emilio López Cano | University of Castilla-La Mancha
senior researcher | Noelia García Rubio | University of Castilla-La Mancha
senior researcher | Matías Gámez Martínez | University of Castilla-La Mancha
senior researcher | Esteban Alfaro | University of Castilla-La Mancha
senior researcher | José Luis Alfaro | University of Castilla-La Mancha
junior researcher | To be contracted | University of Castilla-La Mancha
academic collaborator | Víctor Manuel Casero Alonso | University of Castilla-La Mancha
academic collaborator | Virgilio Gómez-Rubio | University of Castilla-La Mancha
academic collaborator | Javier M. Moguerza | Rey Juan Carlos University
academic collaborator | Andrés Redchuk | Rey Juan Carlos University
industry collaborator | Austin Cox | Honeywell (USA)
industry collaborator | Mariano Prieto | ENUSA (Spain)
industry collaborator | Luc Castermans | Philips (The Netherlands)
industry collaborator | Garry Kitchin | BNL (UK)
industry collaborator | Diana Kardys | u-blox (Switzerland)
academic collaborator | María Villeta | Complutense University
industry collaborator | Juan Riera | Lactalis Groupe

## facts
| Ayudante | CD
Coste anual | 26260.94 | 40000
60% | 15756.564 | 40000
mes | 1432.99
neto mes | 859.794
horas año | 1540 | 1760
coste hora | 10.2315 | 22.7273
horas mes totales | 128.3333 | 146.6667
total horas | 3080 | 528
horas mes proyecto | 128.3333 | 22
c.i. míos | 4160.3333

## Dissemination
stakeholder | web | mail | submission_form
SEIO | http://www.seio.es/ | oficina@seio.es
The World of Statistics | http://www.worldofstatistics.org/ |  | http://www.worldofstatistics.org/wos/submitarticle.cfm